EXECUTIVE STAKEHOLDER PACKAGE | AUGUST 2026

# AI Employment Navigator

Lincoln demonstration -> dedicated implementation -> evidence -> replication

A proposed City of Lincoln / American Job Center Lincoln pathway to translate AI-literacy direction into a practical workforce service, prove it locally, build accountable implementation capacity, and - if evidence supports it - document a model other American Job Centers can evaluate and adapt.

PROJECT ORIGIN & PROPOSED LEADERSHIP The AI Employment Navigator concept, participant workflow, prototypes, implementation framework and initial pilot model were developed by Ryan Uher within American Job Center Lincoln as a proposed workforce innovation. Proposed role: Ryan Uher - Project Lead & Framework Developer. Institutional roles, legal ownership, branding and external use remain subject to City/AJC review and approval.

## The full proposal in one view

| Stage | Duration / status | Purpose |
| --- | --- | --- |
| Phase I | 30-day demonstration | Test workflow, safeguards, usability, lead quality, staff impact and early outcomes. |
| Decision Gate | Executive review | Continue, modify or stop based on evidence, risk, cost and governance readiness. |
| Phase II | 12-18 month implementation pilot | Dedicated implementation capacity; staff training; standardization; expanded measurement; sustainability. |
| Replication Gate | Readiness review | Determine whether evidence, documentation, cost and governance support external replication. |
| Future | Voluntary replication | Package a locally configurable AJC toolkit and share lessons with interested workforce-system partners. |

## Proposed institutional positioning

| Stakeholder | Proposed role |
| --- | --- |
| City of Lincoln / AJC Lincoln | Proposed originating organization and pilot environment |
| Greater Lincoln Workforce Development Board | Potential governance, strategy and scaling partner |
| Ryan Uher | Proposed Project Lead & Framework Developer |
| DOL / ETA | Potential guidance, alignment and technical-assistance partner |
| Future participating AJCs | Potential replication and local-adaptation sites after evidence is established |

PROJECT ORIGIN, ATTRIBUTION & GOVERNANCE

# Preserve institutional credibility and a clear development record

As the initiative moves through additional City, Workforce Board, state and federal discussions, the project should gain institutional governance without losing the documented record of who originated and developed the framework.

Recommended attribution on executive materials AI Employment Navigator - a proposed City of Lincoln / American Job Center Lincoln workforce innovation. Concept, Framework & Prototype Development: Ryan Uher Proposed Project Lead & Framework Developer: Ryan Uher

## Development record

| Development element | Origin / development | Record |
| --- | --- | --- |
| Original concept | Ryan Uher | AI-enabled employment navigation as a practical AJC service model. |
| Participant workflow | Ryan Uher | Candidate profile, privacy choice, master resume, qualified job search, application tailoring and interview preparation. |
| Working prototypes | Ryan Uher | Participant-facing Navigator and supporting implementation/leadership websites. |
| Implementation framework | Ryan Uher | Staff workflow, training approach, safeguards, pilot design and operating documentation. |
| Pilot / evaluation architecture | Ryan Uher | 30-day demonstration, measures, risk controls and decision gates. |
| Replication concept | Ryan Uher | Lincoln-first pathway and locally configurable AJC replication framework. |

## Governance principle

Additional stakeholders should strengthen the initiative through governance, subject-matter expertise, funding, evaluation and authorization. The project record should continue to distinguish institutional sponsorship from individual concept/framework development.

## Recommended documentation practices

Keep Ryan Uher's project role on executive briefs, pilot charters, implementation plans and replication materials.

Use version dates and maintain a controlled project archive of proposals, prototypes, guides and pilot materials.

Create a formal pilot charter that names the executive sponsor, governance partners, Project Lead and decision rights.

Document material changes to the framework and who approved them.

Before making legal ownership or intellectual-property claims, obtain the appropriate City/legal guidance; authorship/contribution and legal ownership are separate questions.

STRATEGIC & FEDERAL ALIGNMENT

# Why now: AI literacy is becoming a workforce-system responsibility

DOL/ETA's February 2026 AI Literacy Framework is directed to American Job Centers, state and local workforce boards, workforce agencies and ETA grantees. It encourages expanded AI education and training and provides a framework for integrating AI literacy into program design.

## Navigator alignment with the DOL framework

| Framework element | Proposed operationalization |
| --- | --- |
| Understand AI principles | Orientation explains capabilities, limits and verification. |
| Explore AI uses | Participants apply AI to real employment tasks. |
| Direct AI effectively | Structured Navigator context replaces ad hoc prompting. |
| Evaluate AI outputs | Participants and staff verify jobs, fit and application content. |
| Use AI responsibly | Privacy choice, minimum-data rules, truthful content and human accountability. |
| Experiential learning | AI literacy is learned through the participant's actual job search. |
| Contextual learning | Learning is embedded in employment-service delivery. |
| Human skills | Judgment, communication, self-advocacy and decision-making remain central. |
| Enabling roles | Career planners receive standardized guidance and training. |
| Agility | Platform-flexible architecture can evolve with technology and policy. |

Federal conversation posture Ask DOL/ETA for guidance on responsible implementation and evaluation - not endorsement. The objective is to make Lincoln's demonstration useful to the broader workforce system while preserving local governance.

PROGRAM LOGIC MODEL

# How the intervention is expected to create value

| Logic model component | Proposed model |
| --- | --- |
| Need | Job seekers face an AI-shaped labor market but vary widely in AI literacy, job-search strategy and access to individualized support. |
| Inputs | AJC staff; Resource Room; approved AI tools; Navigator methodology; NEworks/public job sources; training; governance support. |
| Activities | AI-literacy orientation; profile; master resume; realistic job matching; application tailoring; interview preparation; staff review. |
| Outputs | Profiles; master resumes; qualified leads; applications; interview-prep sessions; staff trained; workflows documented; referrals. |
| Short-term outcomes | AI-literacy confidence; stronger materials; better fit decisions; safer and more independent AI use. |
| Intermediate outcomes | More qualified applications/interviews; appropriate referrals; staff capacity shifted toward higher-value coaching. |
| Long-term outcomes | Employment/retention indicators; sustainable implementation model; documented framework for replication. |

## Core hypotheses

Contextual AI literacy can be delivered effectively through real employment tasks.

A structured Navigator can improve output quality compared with unstructured prompting.

Qualification-based screening can reduce low-value leads without removing participant choice.

Human review and minimum-data rules can support responsible use in a public-workforce setting.

A platform-flexible model can reduce dependence on a single vendor.

Dedicated implementation ownership can improve consistency, adoption, measurement and continuous improvement.

PHASE I | 30-DAY DEMONSTRATION

# Prove the service model before committing to scale

| Track | Illustrative size | Population | Service |
| --- | --- | --- | --- |
| Track A - Universal Access | ~10 | Walk-in / Resource Room job seekers | Navigator setup, AI literacy, master resume, job search, application support |
| Track B - Program Supported | ~10 | Selected participants where appropriate | Navigator integrated into ongoing career-planner support |

## Four-week cycle

| Period | Primary activity |
| --- | --- |
| Week 1 - Build | Governance checklist; staff orientation; baseline; profile/Navigator creation. |
| Week 2 - Pilot | Job discovery; lead verification; applications; workflow observations. |
| Week 3 - Apply | Tailored materials; interview preparation; participant/staff feedback. |
| Week 4 - Measure | Analyze implementation, early outcomes, risk events, time, cost and decision criteria. |

## Decision gate after Phase I

| Decision domain | Evidence reviewed |
| --- | --- |
| Participant value | Completion, usability, AI-literacy change and participant feedback |
| Employment-service quality | Lead quality, application usefulness and early conversion indicators |
| Operational feasibility | Staff time, workflow consistency, accessibility and technology reliability |
| Safety/governance | Privacy, accuracy, bias, misuse and compliance issues |
| Cost | Actual incremental cost and projected cost of continued implementation |
| Strategic value | Evidence that a longer implementation phase could produce meaningful learning |

Decision rule Advance to Phase II only if leadership determines that participant value, governance readiness and implementation feasibility justify a longer pilot. Otherwise modify or stop.

PHASE II | 12-18 MONTH IMPLEMENTATION PILOT

# AI implementation is not a one-time training event. It requires ownership.

If Phase I warrants continuation, the implementation-pilot concept adds the operating layer needed to move from prototype to repeatable service.

Proposed implementation lead: Ryan Uher

Proposed function: AI Workforce Implementation & Employment Specialist

A workforce-development implementation function - not a software-engineering role. Proposed as dedicated capacity during a 12-18 month implementation pilot, subject to organizational approval, classification and funding.

| Responsibility | Phase II function |
| --- | --- |
| Implement | Lead Navigator, Job Watch and approved AI-assisted career-service workflows. |
| Train | Teach job seekers and staff practical AI literacy, prompting, verification and responsible use. |
| Standardize | Create SOPs, guides, workshops, privacy boundaries and human-review procedures. |
| Evaluate | Test tools, document failure points and determine which capabilities create actual workforce value. |
| Measure | Track adoption, lead quality, applications, interviews, placements, time savings and errors. |
| Sustain | Develop grant, partnership and allowable-funding strategies; prepare replication documentation. |
| Report | Provide structured implementation updates and recommendations to executive/governance stakeholders. |

Continuity principle If the project advances, maintaining continuity between original framework development and implementation leadership reduces knowledge loss and preserves accountability while governance expands around the project.

EVALUATION & EVIDENCE

# Measure it like a workforce project, not an AI demo

| Domain | Measure | Source | Cadence |
| --- | --- | --- | --- |
| Reach | Participants served / Navigator completion | Pilot log | Weekly |
| Adoption | Staff trained / approved workflows used | Training + workflow log | Monthly |
| AI literacy | Pre/post confidence and evaluation skills | Participant survey | Entry/exit |
| Quality | Qualified leads vs. poor matches | Staff review log | Weekly |
| Conversion | Applications -> interviews -> offers | Follow-up log | Monthly + follow-up |
| Employment | Placements / retention indicators where available | Approved records/follow-up | 30/60/90 days |
| Efficiency | Staff/client time by workflow stage | Time sample | Monthly |
| Safety | AI errors, privacy issues and corrective actions | Issue register | Continuous |
| Cost | Incremental cost per participant / site | Fiscal + staff time | Quarterly |
| Sustainability | Funding, staffing and operational readiness | Implementation review | Quarterly |
| Replication | Deviations, barriers and local adaptations | Implementation log | Quarterly |

The 30-day phase should be treated primarily as an implementation and early-outcome study, not proof that the Navigator caused employment outcomes. Phase II creates enough time to examine adoption, sustainability, longer-term outcomes and replication readiness more credibly.

GOVERNANCE & RISK

# Responsible AI requires explicit controls

| Risk | Control | Accountability |
| --- | --- | --- |
| Hallucinated/outdated information | Verify against original job posting/source before action. | Staff + participant |
| Fabricated resume content | Truthfulness rule; master resume only from participant-provided information. | Staff + participant |
| PII / sensitive data | Minimum-data design; privacy mode; approved-platform policy; prohibit unnecessary case data. | Privacy / IT |
| Bias / inappropriate screening | Job-related must-have criteria; participant choice; human review; issue logging. | Governance / staff |
| Eligibility/program errors | AI does not make eligibility, benefit, sanction or service-access decisions. | Program leadership |
| Accessibility | Accessibility review; staff-assisted alternative; plain-language materials. | Accessibility / IT |
| Vendor dependence | Platform-flexible methodology; approved-platform list maintained locally. | IT / Project Lead |
| Staff inconsistency | Training, SOPs, demo mode, calibration and quality checks. | Implementation lead |
| Public overstatement | Central communications approval; distinguish proposal, pilot, evidence and replication. | City/AJC communications |
| Security/policy issue | Approved devices/platforms; escalation path; authority to pause. | IT / security |

## Governance gates

Executive sponsor and decision rights

Privacy/security review

Approved-platform position

Accessibility review

Program/compliance boundaries

Fiscal/cost-allocation review

Participant notice/consent approach

Communications/branding approval

Issue escalation and stop-work process

FUNDING & SUSTAINABILITY

# Fund the implementation project - not simply a position

The longer-term case is that responsible AI workforce implementation requires defined activities, deliverables and accountability. Dedicated staffing is an implementation cost needed to train, standardize, govern, measure and document the work.

| Funding pathway | Approach |
| --- | --- |
| Existing infrastructure | AJC staff, computers, Resource Room, NEworks and public job sources - use first where allowable. |
| Existing workforce funds | Explore WIOA, Employment Service, One-Stop/Resource Room or other program costs only after fiscal/compliance review. |
| State innovation | Monitor Nebraska workforce innovation, digital-literacy and technology opportunities. |
| Competitive grants | Evaluate DOL/ETA, reemployment, AI-literacy, workforce-technology and public-sector innovation opportunities. |
| Partners | Higher education, foundations, employers or community organizations may support curriculum, evaluation or technology access. |

Funding guardrail Funding allowability is not assumed. Each cost must be mapped to the underlying service function and reviewed by the appropriate City/AJC fiscal, program, legal and grant-management staff.

## Sustainability questions Phase II must answer

What is the true cost per participant and per site?

What staff capacity is required after the pilot?

Which functions can be embedded in existing roles and which require dedicated capacity?

Which technology/licensing costs are necessary?

What governance functions must remain permanent?

What evidence is strong enough to justify continued or external investment?

REPLICATION ARCHITECTURE

# Standardize the framework. Localize the service.

| Layer | Examples |
| --- | --- |
| Standardized core | Responsible-AI principles; truthfulness; human review; Navigator methodology; minimum metrics; SOP; training; issue logging; fidelity checklist. |
| Locally configurable | Approved AI platforms; state workforce links; local job sources; industries; workshops; contact information; supportive-service pathways; branding. |
| Locally governed | Privacy/security; accessibility; participant notices; program/fiscal use; retention; procurement; public communications. |

## Replication toolkit after successful implementation

Executive adoption brief and readiness assessment

Implementation playbook

Staff training curriculum and demonstration

Participant quick-start materials

Privacy/responsible-AI templates

Local configuration guide

Evaluation dashboard and metric dictionary

Cost model and staffing assumptions

Lessons-learned report

Pilot fidelity / quality-assurance checklist

## Expansion sequence

Lincoln demonstration -> Lincoln implementation pilot -> evidence and refinement -> selected Nebraska/partner validation -> replication toolkit -> voluntary sharing with interested American Job Centers and workforce-system partners.

Attribution in replication materials If the framework advances to replication, retain a project-origin statement identifying Ryan Uher as the original Concept, Framework & Prototype Developer and, if approved, the Project Lead for the Lincoln implementation.

CITY / MAYOR / BOARD / DOL VALUE

# A potential civic-innovation story - if the evidence earns it

| Audience | Potential value |
| --- | --- |
| City of Lincoln | Practical public-service modernization; workforce access; measurable responsible-AI implementation. |
| Mayor's Office | Potential future-ready workforce narrative centered on opportunity, skills and responsible innovation. |
| AJC Lincoln | A repeatable service layer for contextual AI literacy and employment navigation. |
| Workforce Development Board | A locally testable response to changing employment/training needs with measurable outcomes. |
| DOL / ETA | A local implementation example that may generate useful evidence about AI literacy in the public workforce system. |
| Job seekers | A guided, portable way to build AI literacy while improving job-search materials and decisions. |

## Potential future communications

After pilot authorization Lincoln pilots a locally developed, human-led AI employment model designed to help job seekers build AI literacy and navigate an evolving labor market.

If replication follows A workforce-service framework developed and first tested in Lincoln is being evaluated for use by additional American Job Centers.

Any reference to the City, Mayor, Workforce Board, DOL, 'pioneering,' 'first,' or national significance should be cleared through the appropriate communications and governance process before public use.

## Project attribution for public-facing materials

Where appropriate and approved, communications should distinguish the institutional initiative from its development record:

City of Lincoln / American Job Center Lincoln - proposed originating organization and pilot site
Ryan Uher - Concept, Framework & Prototype Developer; Proposed Project Lead

EXECUTIVE ACTION & DOL CONVERSATION

# Recommended decisions and next steps

1. Identify an executive sponsor and cross-functional governance reviewers.

2. Recognize the documented project origin and proposed Project Lead role in the pilot charter and executive materials.

3. Authorize completion of the final 30-day pilot protocol and readiness checklist.

4. Confirm implementation decision rights and reporting structure.

5. Engage the appropriate DOL/ETA Regional Office for guidance.

6. Brief appropriate City and Workforce Board stakeholders on the demonstration opportunity.

7. Complete privacy, security, accessibility, compliance, fiscal and communications review.

8. Launch only after governance gates are satisfied.

9. Return with a written Phase I report before deciding on the 12-18 month implementation phase.

10. If Phase II is approved, formalize dedicated implementation capacity, role responsibilities, measures and funding.

11. Consider replication only after evidence and readiness criteria are met.

## Suggested DOL / ETA framing

Conversation opener Lincoln is considering a controlled demonstration of a human-led AI employment-service framework that embeds AI literacy into job-search preparation. The concept and initial framework were developed locally within AJC Lincoln. We are seeking guidance on responsible implementation, evaluation, applicable workforce-system requirements, and how lessons could be shared if the demonstration produces value.

## Authoritative reference basis

U.S. Department of Labor, Employment and Training Administration - Training and Employment Notice 07-25, AI Literacy Framework (February 13, 2026).

U.S. Department of Labor / ETA workforce-innovation evaluation materials addressing implementation, logic models, outputs, outcomes, sustainability, replication and lessons learned.

American Job Center Lincoln / City of Lincoln Future-Ready Workforce materials for local workforce context.

LINCOLN FIRST. EVIDENCE FIRST. REPLICATION BY DESIGN.

Concept, Framework & Prototype Development: Ryan Uher